## Sheet1
Sprint Backlog Template

Backlog Item	Story Points	Responsible	Status	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5	Sprint Review
User Story #1	8
Task				7	5	3	0	0	0	0
Task				3	1	1	5	0	1	0	Sprint Burndown
Task				1	0.5	0	3	0	0	0
Task				0.5	1	2	3	1	0	0
Anna's User Story	1
Weather read from JSON file – simple		AR	Completed	2	3	0	0	0	0	0
Adding weather icons		AR	Completed	1	0	4	0	0	0	0
Filtering JSON records by date		AR	Completed	3	0	0	2	2	0	0
Filtering JSON records by location		AR	Completed	3	0	0	0	0	3	0
User Tests		AR	Completed	3	0	0.5	0.5	0.5	1.5	0
User Story #3	5
Task				8	6	0	0	0	0	0
Task				3	1	3	3	3	0	0
Task				1.5	1	0.5	0.5	1	1	0
Task				2	0.5	0	0	0	0	3
User Story #4	8
Task				9	4	2	2	1	1	0
Task				6	6	3	3	3	1	1
Task				6	2	8	8	1	0	1
Task				0.5	0.5	0.5	0.5	0	0	0
User Story #5	3
Task				2	1	1	1	0.5	1	1
Task				6	6	6	0.5	3	9	0
Task				9	9	9	4	3	3	3
Task				0.5	0.5	0.5	1	0.5	0	1
Total				77	48	44	37	19.5	21.5	10

Create a Sprint Backlog in Smartsheet